## Sheet1
Date | Module | Defect Type | Severity | Status | Notes
2025-04-01 | Login | Login failure | High | Open | Multiple login failures post-security update
2025-04-02 | Registration | Field validation error | Medium | Resolved | Phone number field accepting letters
2025-04-03 | Registration | Incorrect error message | Low | Resolved | Error message on password mismatch unclear
2025-04-04 | Claims Module | Crash on claim submission | Critical | Open | App crashes when submitting a new claim
2025-04-05 | Dashboard | Display bug | Low | Closed | Icons misaligned on dashboard page
2025-04-08 | Login | Session timeout | Medium | Resolved | Session expires after 2 minutes idle
2025-04-10 | Claims Module | Incorrect claim status update | High | Open | Claim status remains 'Pending' after approval
2025-04-12 | Dashboard | Broken link | Low | Closed | Help link on dashboard leads to 404 page
2025-04-15 | User Profile | Profile picture upload failure | Medium | Resolved | Profile picture upload hangs indefinitely
2025-04-16 | User Profile | Profile info not saving | High | Open | Changes to user info not saved correctly
2025-04-18 | Login | Multi-factor authentication failure | Critical | Open | MFA code not accepted despite correct entry
2025-04-20 | Claims Module | Slow claim processing | Medium | Resolved | Claims take over 2 minutes to process